## Slide 1: MSc IT+ Projects Tracker
Gül ÇALIKLI
(original slides by John Hill & Mark McGill)

## Slide 2: Project Ideation
To be completed by May 29th
Download a copy of this tracker to your University OneDrive account.
Fill in the “About You” and “Project Ideation” sections out by May 29th and share the live “edit” link to your project tracker with us via Microsoft Forms. This is so your supervisor (once assigned) can access this over the course of your project.

## Slide 3: About You This information will help your supervisor to understand your background, skillset and interests Optional – Include a photo of yourself below
Question | Your Response
Is there a name other than your first name as noted with the University that you would prefer to be used by your supervisor in your contact with them? | Please call me Faye.
Please state your previous degree topic and any other relevant background information you would like your supervisor to know. | Bachelor of Economics. After graduation, 7 years in digital media operations, with day-to-day work centered on data analysis and operational decision-making.
Please state what previous programming experience (languages, frameworks etc) that you have beyond the current MSc IT+ degree, if any. | Python (Pandas, NumPy), SQL, Java, Django. Comfortable with Git and Linux basics. Plan to add Power BI (or Tableau) and LLM API integration through this project.
Please briefly note what future career aspirations you have (e.g. programmer, business analyst, consultant, ...), and what job role you are targeting (e.g. finance, government, technology, academia, ...) after this degree. | Primary goal: Business Intelligence Analyst or Data Analyst roles, combining 7 years of business experience with the technical skills built during this degree. I prefer roles centered on data and analysis. Secondary directions: Business Analyst, Technical Product Manager, or Junior Software Engineer.

## Slide 4: Project Topic Ideation Based on the project Ideation video, try to see if you can define a project topic. Your supervisor will then provide feedback on your topic ideas, and prescribe a topic if necessary, by Week 1 of the IT+ projects.
Question | Your Response
For your individual development project, is there any particular platform you want to gain experience developing for (e.g. Web apps, Mobile apps, Desktops apps, Services and APIs, Cloud apps/infrastructure etc.)? | Web application — Python backend + browser-based dashboard, with part of the analytical logic exposed as an API.
Is there any particular technology or application type you want to focus on (e.g. games, responsive web apps, machine learning etc.) | Data analytics + AI integration. Stack: SQL on a cloud data warehouse (BigQuery or Snowflake free tier), Python (Pandas), Power BI (or Tableau), and LLM API integration. Includes statistical analysis (e.g. A/B testing). Some tools (cloud warehouse, Power BI, LLM integration) are new to me — learning them is part of the project goal.
Is there a particular subject area that you want your project to work within e.g. business, ecology, sports, travel, entertainment etc. | Open. Prefer a public dataset (e.g. Kaggle, UK open data) with enough complexity for meaningful analysis — e.g. e-commerce, retail, or public services.
Do you have a project idea in mind that you'd want to pursue? If so, in a few sentences describe: what the development project would aim to produce why you want to pursue this your initial thoughts on the high level requirements that your project could potentially address | What: An end-to-end data analytics web application. It ingests a public dataset, models it in SQL, runs analytical workflows in Python, presents results through an interactive dashboard, and exposes a natural-language query interface powered by an LLM API. Why: To build a complete project covering data, analytics, visualization, and AI integration in one system. Some components are new skills I want to develop through this project. Requirements: SQL data modeling; Python analysis (including A/B testing and simple forecasting); interactive dashboard; LLM-based natural-language query layer; evaluation of analytical accuracy and LLM query reliability
Would you be interested in working on a development project with a pre-existing customer within the University (e.g. a School needing a specific web app to be built) | Yes

## Slide 5: Project Topic Ideation Feedback from Supervisor
Overall Evaluation: The supervisor confirmed that the general direction of the project topic is good and represents a highly promising start.
Scope Refinement (Key Action Item): Need to drill down into the specific details before the next meeting to clearly define the exact project scope (determining what will be included and what will be excluded).
Next Steps: Focus on defining the detailed project requirements once the scope is finalized.
Communication & Follow-up: Utilize the dedicated MS Teams channel to raise any interim questions or share ideas prior to the next 1-to-1 meeting at the end of June.

## Slide 6: Project Proposal
To be updated as the topic and scope become clearer from Week 1 onwards

## Slide 7: Proposed Project Based on the feedback and discussion with your supervisor, now refine your understanding of your project topic and aims. This should be agreed with your supervisor by the start of Week 2 at the latest.
Question | Your Response
What type of application (e.g. Web app, Mobile app, Desktops app, Service/API, Cloud app etc.) are you going to develop? | A web application — a configurable self-serve data-analysis product. You upload data tables and declare what each column means (role + join key) with no code; the system progressively unlocks the matching analyses (KPIs, cohort, RFM…). Being config-driven (not hard-coded to one domain) it works across domains, with built-in models per domain (deeply demonstrated on e-commerce + a 2nd domain). A natural-language (NL→SQL) layer lets non-technical users query directly; it also supports multiple parallel projects.
What technologies are you going to develop using? (e.g. what framework, stack, programming languages etc). If these are technologies other than what you have gained experience with through the MSc IT+ course, justify this. | Stack: Python (Pandas), PostgreSQL, Streamlit, an LLM API, Power BI, Git/GitLab. New beyond the course — PostgreSQL, Streamlit, Power BI — chosen as the stack for my target BI / Data Analyst roles (Power BI is a top-requested DA skill; PostgreSQL is an industry-standard free DB). I use Streamlit, not Django (which I know), because Django suits full websites while Streamlit is lightweight and builds the data app + LLM query UI directly in Python.
Describe your project topic and aims, considering: what the development project would aim to produce why you want to pursue this your initial thoughts on the high level requirements that your project could potentially address | What it produces: a configurable self-serve data-analysis product. You upload tables; the tool auto-profiles & cleans them (AI-assisted suggestions, flag to confirm), then you declare each column's role + join key (no code); the system progressively unlocks the matching analyses (KPIs, cohort, RFM…) as joinable data arrives. Being config-driven, it works across domains, demonstrated deeply on e-commerce + a 2nd domain. A natural-language layer (NL→SQL, shows the SQL) lets non-technical users ask directly. Why: builds the exact stack for my target BI / Data Analyst roles; and offers accessible AND trustworthy self-serve analytics (transparent, self-hostable, no-code) vs closed enterprise tools and risky “paste-into-a-chatbot” analytics. Key requirements: • Upload: profile + auto-clean (flag issues to confirm) + no-code semantic config (roles + join keys) • Data registry + progressive-unlock engine • Multi-domain analysis templates (e-commerce + a 2nd domain) • Natural-language query (NL→SQL, safe, shows SQL) + dashboard • Multi-project support (parallel projects) • Evaluation: benchmark + a small user study

## Slide 8: Changes to Proposed Project As you progress through the 12 week project, keep a note of any changes to the proposed project topic, aims, technologies used etc. here. This will help your supervisor to understand how the project has evolved and why.
How did the project topic / aims / objectives change? | When did this change occur? (week / date) | Why did you make this change? | Has this been discussed with Supervisor?

## Slide 9: URLs / Resources Link to any useful URLs and resources you want to share directly with your supervisor here. This should include a link to your Gitlab repository (once setup by end of Week 1) and the latest working copy of your dissertation (e.g. on Onedrive, Overleaf etc).
Gitlab repository: https://stgit.dcs.gla.ac.uk/msc-project-for-information-technology/2025/it-project-3155021y/self-serve-analytics
Dissertation:

## Slide 10: Project Architecture Diagram Add and maintain an architecture diagram to help your supervisor understand your project design and approach
User — analyst / non-technical business user
PRESENTATION
Streamlit web app — dashboard + natural-language query (shows the generated SQL)
Power BI — business dashboard
LOGIC — Python backend
Profiling + auto-clean · semantic config (roles + join keys) · data registry · progressive-unlock engine · analysis templates (KPIs/cohort/RFM)
NL→SQL engine · query validation (read-only) · evaluation harness
LLM API (external)
writes SQL + suggests cleaning
DATA
PostgreSQL — star-schema data model
Source: Olist e-commerce dataset (CSV)
Flow: question → Streamlit → backend → LLM writes SQL → validated & run on PostgreSQL → result + SQL shown back. A standard 3-tier architecture (presentation / logic / data).

## Slide 11: Weekly Progress Tracker To be filled out by the student every week, tracking progress, aims, issues, and planning your agenda for any meetings with your supervisor or GTAs.

## Slide 12: Purpose of the Progress Tracker
The progress tracker is here to help you manage your project – to set targets, explore expectations and aims with your supervisor, and organise and document your thoughts and progress along the way
Each week has an associated progress tracker slide that should be filled out week-by-week.
There are also “status update” slides aligned with the mandatory supervisor meetings throughout the project. These should also be filled prior to meeting your supervisor to evidence your progress.
You can modify this template! Adapt it to suit your project needs as you go!
Filling out the Weekly Progress Tracker and Status Update slides is mandatory – If you don’t fill this material out, this will count against your professional conduct grade, and if you can’t evidence you’ve conducted the project independently, we may refuse to mark any submission.

## Slide 13: Example
Key Milestones | Status
Project Topic & High Level scope | Complete and written up
Requirements / Analysis | In progress but not written up
Tools, Stack, Dev. Environment | 
Prototype and Design | 
Development | 
System testing | 
User Evaluations | 
Dissertation & Video | 
 | Not Started
 | On track
 | Issues
 | Major issues
 | Completed
Key
Completed Activities This week
Completed Internet search of similar systems Developed personas to drive requirements
Meeting Agenda (if scheduled for this week)
Key Points… …that you want to cover… …for this weeks meeting with your supervisor, or with a GTA in the lab.
Issues, Risks and Concerns
Trying to decide between Django and Flask for the most appropriate Python framework Trying to decide between MySQL and PostgreSQL as the database
Upcoming Activities – Next week
User interface design Database design

## Slide 14: Week 1 – Initial Supervisor Meeting
Key Milestones | Status
Project Topic & High Level scope | On track
Requirements / Analysis | On track
Tools, Stack, Dev. Environment | On track
Prototype and Design | Not Started
Development | Not Started
System testing | Not Started
User Evaluations | Not Started
Dissertation & Video | Not Started
 | Not Started
 | On track
 | Issues
 | Major issues
 | Completed
Key
Completed Activities This week
• Defined & scoped the project: a configurable self-serve analytics product (no-code config + a progressive-unlock engine + multi-domain analyses + NL→SQL), demonstrated on e-commerce (Olist) + a 2nd domain. • Researched competitors (Power BI Copilot, ThoughtSpot, Vanna, WrenAI) and candidate datasets. • Drafted the Proposed Project + a one-page brief.
Meeting Agenda (if scheduled for this week)
Kick-off with supervisor: 1) Scope/feasibility of the full version (configurable progressive-unlock multi-domain + NL query) — MVP vs stretch 2) Plan: Olist (e-commerce) + a public/synthetic finance dataset; local PostgreSQL; Streamlit 3) Evaluation: technical benchmark + a small user study — confirm ethics route 4) Set up GitLab repo this week 5) Agree plan for Weeks 2–4 (requirements & design)
Issues, Risks and Concerns
• Main technical uncertainty — how accurately the LLM turns questions into correct SQL on this dataset is not known in advance; to be measured with a benchmark, with safeguards (read-only, query validation). • If a user study is included, ethics approval should be started early so it does not delay the evaluation.
Upcoming Activities – Next week
• Finalise scope with supervisor. • Set up GitLab repo + dev environment (Python, PostgreSQL). • Requirements: user stories, MoSCoW, personas & use cases; competitor analysis; background reading (Zotero). • Design: architecture, data model (ER with a project/workspace entity + table relationships), the unlock-engine logic, UML, UI wireframes. • Acquire & explore Olist; find a public finance dataset for project 2.

## Slide 15: Week 2
Key Milestones | Status
Project Topic & High Level scope | 
Requirements / Analysis | 
Tools, Stack, Dev. Environment | 
Prototype and Design | 
Development | 
System testing | 
User Evaluations | 
Dissertation & Video | 
 | Not Started
 | On track
 | Issues
 | Major issues
 | Completed
Key
Completed Activities This week
Meeting Agenda (if scheduled for this week)
Issues, Risks and Concerns
Upcoming Activities – Next week

## Slide 16: Week 3/4 Status Update Requirements, Design
Project topic & scope are locked: a configurable, self-serve data-analysis product. Users upload data; the tool auto-profiles and cleans it (flagging issues to confirm), lets them tag columns with roles (no code), then progressively unlocks role-based analyses (KPIs, cohort, RFM) and answers natural-language questions via a transparent NL→SQL engine that shows the SQL. It is demonstrated on the Olist e-commerce dataset and generalises to other domains by configuration alone.
Requirements (Analysis) are complete: 2 personas; 21 user-story cards prioritised with MoSCoW (13 Must = MVP); 2 end-to-end scenarios; 8 measurable non-functional requirements; and a competitor/related-work review (Power BI Copilot, Tableau, ThoughtSpot, open-source Vanna/WrenAI) framing the contribution as transparency, evaluation and integration rather than novelty.
Design is complete: a three-tier architecture (Streamlit + Power BI / Python / PostgreSQL); a domain-independent meta-model (ER) and the Olist logical star schema; the engine logic as pseudocode and flowcharts (progressive-unlock check; config-driven NL→SQL with read-only + whitelist validation; profiling/cleaning); a UML class diagram; and six UI wireframes.
Key decision: the engine is config-driven with no per-domain code, so it generalises across domains. Next: set up the GitLab repo + dev environment and begin the MVP build in Week 5.

## Slide 17: Week 3
Key Milestones | Status
Project Topic & High Level scope | 
Requirements / Analysis | 
Tools, Stack, Dev. Environment | 
Prototype and Design | 
Development | 
System testing | 
User Evaluations | 
Dissertation & Video | 
 | Not Started
 | On track
 | Issues
 | Major issues
 | Completed
Key
Completed Activities This week
Meeting Agenda (if scheduled for this week)
Issues, Risks and Concerns
Upcoming Activities – Next week

## Slide 18: Week 4
Key Milestones | Status
Project Topic & High Level scope | 
Requirements / Analysis | 
Tools, Stack, Dev. Environment | 
Prototype and Design | 
Development | 
System testing | 
User Evaluations | 
Dissertation & Video | 
 | Not Started
 | On track
 | Issues
 | Major issues
 | Completed
Key
Completed Activities This week
Meeting Agenda (if scheduled for this week)
Issues, Risks and Concerns
Upcoming Activities – Next week

## Slide 19: Week 5
Key Milestones | Status
Project Topic & High Level scope | Completed
Requirements / Analysis | Completed
Tools, Stack, Dev. Environment | Completed
Prototype and Design | Completed
Development | On track
System testing | Not Started
User Evaluations | Not Started
Dissertation & Video | Not Started
 | Not Started
 | On track
 | Issues
 | Major issues
 | Completed
Key
Completed Activities This week
• Completed all Requirements & Design: 2 personas; 21 user-story cards + MoSCoW (13 Must = MVP); 8 NFRs; 2 scenarios; architecture; data model (meta-model ER + Olist star); engine logic (unlock, NL→SQL, cleaning) as pseudocode + flowcharts; UML class diagram; 6 UI wireframes. • Set up GitLab repository + development environment.
Meeting Agenda (if scheduled for this week)
Meeting plan: 1) Recap progress — Requirements & Design are complete . 2) Feedback & confirm —Confirm MVP scope + the config-driven approach. 3) Next phase — plan to begin development (MVP build); 2nd-domain dataset; timeline.
Issues, Risks and Concerns
• NL→SQL accuracy on unfamiliar schemas is an empirical risk — to be quantified in evaluation. • Keeping the generic engine from eating into e-commerce depth within the timeline.
Upcoming Activities – Next week
• Begin building the MVP core (Prototyping & Build): data upload, profiling/cleaning, semantic config, progressive-unlock engine. • Start drafting the Analysis & Design chapters from the collected material.

## Slide 20: Week 6/7 Status Update
Final design and aims: unchanged since the Week 3/4 review — a configurable self-serve analytics tool. Users upload CSV files, the tool profiles and cleans them, the user describes each column by role and join key with no code, role-based analyses (Key metrics, Cohort, RFM) unlock progressively, and natural-language questions are answered through a transparent NL→SQL path that always shows the SQL.
Prototyping and build: the core engine was built first (weeks 5–6) — domain model, DuckDB registry, profiling, cleaning, semantic configuration with auto-suggested roles and keys, the unlock engine with lock reasons, and config-driven SQL for the three templates. The full MVP now runs end to end: upload wizard, dashboard with Plotly charts, and the Ask screen. The NL→SQL layer has an offline stub and an optional OpenAI client behind one interface, a read-only SQL validator built on sqlglot, and a query history that stores the SQL so re-runs skip the model. Live demonstration in the meeting.
Dissertation: outline agreed; requirements and design written up in the Week 3–5 pack, to become Chapters 2–3 once the build settles.

## Slide 21: Week 6
Key Milestones | Status
Project Topic & High Level scope | 
Requirements / Analysis | 
Tools, Stack, Dev. Environment | 
Prototype and Design | 
Development | 
System testing | 
User Evaluations | 
Dissertation & Video | 
 | Not Started
 | On track
 | Issues
 | Major issues
 | Completed
Key
Completed Activities This week
Meeting Agenda (if scheduled for this week)
Issues, Risks and Concerns
Upcoming Activities – Next week

## Slide 22: Week 7
Key Milestones | Status
Project Topic & High Level scope | Completed
Requirements / Analysis | Completed
Tools, Stack, Dev. Environment | Completed
Prototype and Design | Completed
Development | On track
System testing | On track
User Evaluations | Not started
Dissertation & Video | Not started
 | Not Started
 | On track
 | Issues
 | Major issues
 | Completed
Key
Completed Activities This week
• Built full MVP end-to-end: upload → clean → no-code config → progressive-unlock dashboard → NL→SQL • NL→SQL shows/downloads the generated SQL; read-only SQL validator; query history persisted to a DuckDB file • Started pytest suite ; fixed bugs found while testing the prototype
Meeting Agenda (if scheduled for this week)
• Live demo of the MVP (upload → configure → dashboard → NL→SQL with visible SQL)
Issues, Risks and Concerns
Upcoming Activities – Next week
• Finish unit tests + project wrap-up • Start the dissertation draft (intro, background, requirements & design) • If time: second-domain generalisation test

## Slide 23: Week 8/9 Status Update
Build: at the minimum viable product and beyond it. Since the last meeting — cleaning made opt-in as suggested (detect → explain → apply only what the user approves); projects and query history persist across restarts; accounts, sign-in and multiple projects with a database file per project; cross-table SQL from declared join keys; deployed to Streamlit Community Cloud with a daily cap on model calls; dark theme and an animated landing page.
Remaining development: finish the test suite and a wording pass so that lock reasons use plain words rather than role names.
Evaluation plan: (1) automated tests — unit tests for pure logic, integration tests through DuckDB, the file system and the Streamlit app; (2) requirement coverage, US1–US22 and NFR-1–5, against evidence; (3) a ~30-question NL→SQL benchmark on the study data, offline stub as the baseline against gpt-4o-mini; (4) an unmoderated remote user study — a 13-step task sheet, two data files split so that progressive unlock is exercised, and an anonymous Forms survey with five project statements plus SUS (ethics checklist signed).
Dissertation: Chapters 2–3 drafted from the design pack; test statistics and the survey design on the next two slides.

## Slide 24: Week 8
Key Milestones | Status
Project Topic & High Level scope | 
Requirements / Analysis | 
Tools, Stack, Dev. Environment | 
Prototype and Design | 
Development | 
System testing | 
User Evaluations | 
Dissertation & Video | 
 | Not Started
 | On track
 | Issues
 | Major issues
 | Completed
Key
Completed Activities This week
Meeting Agenda (if scheduled for this week)
Issues, Risks and Concerns
Upcoming Activities – Next week

## Slide 25: Week 9
Key Milestones | Status
Project Topic & High Level scope | Completed
Requirements / Analysis | Completed
Tools, Stack, Dev. Environment | Completed
Prototype and Design | Completed
Development | Completed
System testing | Completed
User Evaluations | On track
Dissertation & Video | Not started
 | Not Started
 | On track
 | Issues
 | Major issues
 | Completed
Key
Completed Activities This week
• Test suite finished: 117 cases, all passing • Task sheet, survey (live in Forms) and study dataset ready — the data is split in two so progressive unlock is exercised • Accounts and a redesigned landing page: register, sign in, UI polish across the app • Multiple projects per account, each with its own data and history
Meeting Agenda (if scheduled for this week)
• Walk through the test suite • Review the draft task sheet and survey
Issues, Risks and Concerns
Upcoming Activities – Next week
• Run the user study (target 3-5 participants, mixed SQL experience) • Start the dissertation draft: Introduction, Background/Analysis, Design • Build the requirements-coverage table (US1–US20, NFR-1–5) and a ~30-question NL→SQL benchmark • Draft the demo video script

## Slide 26: unit test
117 tests, all passing · 96% coverage of the service layer, 91% of the core package, 70% overall
• Service layer Covered: profiling, cleaning, semantic configuration, unlock engine, analysis templates, SQL guard, accounts, project isolation, NL→SQL, usage cap
• Unit tests for the pure logic; integration tests run against a real DuckDB, real files, and the whole Streamlit app
• openai_client.py is 0% by design — it only calls the OpenAI API; tests use a stub with the same interface, so they stay fast, free and repeatable
• The rest of the gap is error-handling branches — a corrupt row, a locked file, SQL the parser itself cannot read
• The UI layer is 44%: routing and session state are covered, visual appearance is not — the user study judges that instead

## Slide 27: Survey
https://forms.cloud.microsoft/e/H0nvCdQ6Nm
The survey — Forms, anonymous, ~4 min
• Consent, then one background question: the participant's SQL level
• Five statements written for this project: unlock, describing columns, seeing the SQL, control over cleaning, trust
• The System Usability Scale — ten standard statements, scored 0–100
• SUS is used because it is standard: the score compares against a published benchmark of 68. It must be used whole
• Two optional free-text boxes: what was good, what could be improved
The task sheet — 13 steps, ~20 min, unmoderated
• Participants get the app and two data files and work alone, so the study can run remotely
• Every step says what to do and what to notice
• The data is split in two on purpose: the first file has no amounts, so only Cohort unlocks
• Step 6 stops there — whether the lock reason makes sense is the key observation
• The second file unlocks the rest;
• Target: 5 participants, mixed SQL experience

## Slide 28: Week 10/11 Status Update
By the Week 10/11 meeting, you should be able to update your supervisor on:
  The results of any evaluations and testing conducted or in-progress
  Remaining dissertation writing (e.g. evaluation, discussion, conclusions), and your plan for the last 2 weeks and final write-up.
  Any remaining content you would like supervisor feedback on, if they have time.

## Slide 29: Week 10
Key Milestones | Status
Project Topic & High Level scope | 
Requirements / Analysis | 
Tools, Stack, Dev. Environment | 
Prototype and Design | 
Development | 
System testing | 
User Evaluations | 
Dissertation & Video | 
 | Not Started
 | On track
 | Issues
 | Major issues
 | Completed
Key
Completed Activities This week
Meeting Agenda (if scheduled for this week)
Issues, Risks and Concerns
Upcoming Activities – Next week

## Slide 30: Week 11
Key Milestones | Status
Project Topic & High Level scope | Completed
Requirements / Analysis | Completed
Tools, Stack, Dev. Environment | Completed
Prototype and Design | Completed
Development | Completed
System testing | Completed
User Evaluations | Completed
Dissertation & Video | On track
 | Not Started
 | On track
 | Issues
 | Major issues
 | Completed
Key
Completed Activities This week
• 30-question NL→SQL benchmark: gpt-4o-mini 80% vs offline stub 13%, failures classified; two stub defects fixed; second-domain check on a synthetic hospital dataset (6 Sep) • Per-card column selector for each role (2 Sep); named shared join keys; requirements-lock.txt • Tests: 126 cases pass in 2.3 s; 92% coverage of ssa, 97% of the service layer • Dissertation: full draft Ch1–5 + 26 verified references in the School template (19 pages); video script drafted
Meeting Agenda (if scheduled for this week)
No meeting this week (viva done at the Week 10/11 checkpoint)
Issues, Risks and Concerns
Upcoming Activities – Next week
• Record the 10-minute solution video (face on camera) • Final proofread, contents, export the PDF • Package the zip (code, CodeList, SoftwarePrereqs, task sheet, survey, ethics, tracker); sign the originality form • Submit on Moodle by Fri 11 Sep 16:30

## Slide 31: Week 12 - Final Week
Key Milestones | Status
Project Topic & High Level scope | 
Requirements / Analysis | 
Tools, Stack, Dev. Environment | 
Prototype and Design | 
Development | 
System testing | 
User Evaluations | 
Dissertation & Video | 
 | Not Started
 | On track
 | Issues
 | Major issues
 | Completed
Key
Completed Activities This week
Meeting Agenda (if scheduled for this week)
Issues, Risks and Concerns
Activities Remaining